## Sheet1
|  | Week 1 / Jun | [6 empty] | Week 2 / May | [6 empty] | Week 3 / Jun-July | [6 empty] | Week 4 /July | [6 empty] | Week 5 /July | [6 empty] | Week 6 /July | [6 empty] | Week 7 /July | [6 empty] | Week 8 /July-August | [6 empty] | Week 9 /August | [6 empty] | Week 10 /August | [6 empty] | Week 11 /August | [6 empty] | Week 12 /August-September | [6 empty] | Week 13 /September | [6 empty] | Week 14 /September | [6 empty] | Week 15 /September | [6 empty] | Week 16 /September-Oct | [6 empty] | Week 17 /October | [6 empty] | Week 18 /October | [6 empty] | Week 19 /October | [6 empty] | Week 20 /October | [6 empty] | Week 21 /October-November | [6 empty] | Week 22 /November | [6 empty] | Week 23 /November | [6 empty] | Week 24 /November | [6 empty] | Week 25 /November-Dec | [6 empty] | Week 26 /December | [6 empty] | Week 27/December | [6 empty] | Week 28
item | scope of work | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | start of construction | bar: Week 1 / Jun 12
2 | Permits - insurance | bar: Week 1 / Jun 12 to Week 1 / Jun 13
3 | Site prep for demolition | bar: Week 1 / Jun 14
4 | Remove appliances, fixture, etc | bar: Week 1 / Jun 15 to Week 1 / Jun 17
5 | Remove finishes | bar: Week 1 / Jun 17; Week 2 / May 19 to Week 2 / May 20
6 | Remove non load bearing walls | bar: Week 2 / May 21 to Week 2 / May 24; Week 3 / Jun-July 26 to Week 3 / Jun-July 27
7 | Remove HVAC,Elect,etc | bar: Week 3 / Jun-July 27 to Week 3 / Jun-July 1
8 | Site cleaning | bar: Week 4 /July 3
9 | Concrete floor patching | bar: Week 4 /July 4
10 | Steel stud framing walls | bar: Week 4 /July 5 to Week 4 /July 8; Week 5 /July 10 to Week 5 /July 15; Week 6 /July 17 to Week 6 /July 22; Week 7 /July 24 to Week 7 /July 28
11 | Steel stud framing ceilings | bar: Week 7 /July 24 to Week 7 /July 28
12 | Rough in Plumbing | bar: Week 7 /July 24 to Week 7 /July 26; Week 8 /July-August 31 to Week 8 /July-August 5; Week 9 /August 7 to Week 9 /August 12; Week 10 /August 14 to Week 10 /August 18; Week 11 /August 24 to Week 11 /August 26
13 | Rough in Electrical | bar: Week 5 /July 13 to Week 5 /July 14; Week 6 /July 21 to Week 6 /July 22; Week 8 /July-August 31 to Week 8 /July-August 5; Week 9 /August 7 to Week 9 /August 12; Week 10 /August 14 to Week 10 /August 19; Week 11 /August 21 to Week 11 /August 26; Week 12 /August-September 28 to Week 12 /August-September 2
14 | Rough in HVAC | bar: Week 5 /July 13 to Week 5 /July 14; Week 6 /July 20 to Week 6 /July 21; Week 7 /July 24 to Week 7 /July 28; Week 8 /July-August 31 to Week 8 /July-August 4; Week 9 /August 7 to Week 9 /August 11; Week 10 /August 14 to Week 10 /August 18; Week 11 /August 21 to Week 11 /August 25; Week 12 /August-September 28 to Week 12 /August-September 2
15 | Rough in Sprinkler | bar: Week 5 /July 13 to Week 5 /July 14; Week 6 /July 20 to Week 6 /July 21; Week 8 /July-August 31 to Week 8 /July-August 4; Week 9 /August 7 to Week 9 /August 12; Week 10 /August 14 to Week 10 /August 19; Week 11 /August 21 to Week 11 /August 26; Week 12 /August-September 28 to Week 12 /August-September 2
16 | Rough in Fire alarm | bar: Week 6 /July 20 to Week 6 /July 21; Week 11 /August 23 to Week 11 /August 25; Week 12 /August-September 30 to Week 12 /August-September 1
17 | Rough in Low voltage | bar: Week 8 /July-August 31 to Week 8 /July-August 2; Week 9 /August 9 to Week 9 /August 11; Week 10 /August 16 to Week 10 /August 18; Week 11 /August 23 to Week 11 /August 25; Week 12 /August-September 30 to Week 12 /August-September 1
18 | Rough in inspections | bar: Week 10 /August 16 to Week 10 /August 17; Week 12 /August-September 28 to Week 12 /August-September 1
19 | Insulation | bar: Week 13 /September 4 to Week 13 /September 9; Week 14 /September 11 to Week 14 /September 16; Week 15 /September 18 to Week 15 /September 23
20 | Drywall | bar: Week 13 /September 4 to Week 13 /September 9; Week 14 /September 11 to Week 14 /September 16; Week 15 /September 18 to Week 15 /September 23
21 | Skim coat | bar: Week 13 /September 4; Week 14 /September 11 to Week 14 /September 16; Week 15 /September 18 to Week 15 /September 23
22 | Prep walls | bar: Week 13 /September 4; Week 14 /September 11 to Week 14 /September 16; Week 15 /September 18 to Week 15 /September 23
23 | Order glass walls / doors | bar: Week 14 /September 11 to Week 14 /September 12
24 | floor finishes (tiles) | bar: Week 16 /September-Oct 25 to Week 16 /September-Oct 30; Week 17 /October 2 to Week 17 /October 7; Week 18 /October 9 to Week 18 /October 14
25 | wall finishes (tiles) | bar: Week 16 /September-Oct 25 to Week 16 /September-Oct 30; Week 17 /October 2 to Week 17 /October 7; Week 18 /October 9 to Week 18 /October 14
26 | Ceiling framing | bar: Week 16 /September-Oct 25 to Week 16 /September-Oct 30; Week 17 /October 2 to Week 17 /October 7; Week 18 /October 9 to Week 18 /October 14
27 | Door frames | bar: Week 16 /September-Oct 25 to Week 16 /September-Oct 30; Week 17 /October 2 to Week 17 /October 7; Week 18 /October 9 to Week 18 /October 14
28 | Rough in cabinetry | bar: Week 18 /October 12 to Week 18 /October 14; Week 19 /October 16 to Week 19 /October 21; Week 20 /October 23 to Week 20 /October 28
29 | Painting | bar: Week 19 /October 16 to Week 19 /October 21; Week 20 /October 23 to Week 20 /October 28
30 | Millwork finishes | bar: Week 20 /October 23 to Week 20 /October 28
31 | Sprinkler finishes | bar: Week 21 /October-November 30 to Week 21 /October-November 3
32 | Plumbing finishes | bar: Week 21 /October-November 30 to Week 21 /October-November 1; Week 22 /November 7 to Week 22 /November 9
33 | Install accoustical ceiling | bar: Week 20 /October 23 to Week 20 /October 28; Week 21 /October-November 30 to Week 21 /October-November 3
34 | Carpet | bar: Week 22 /November 6 to Week 22 /November 10; Week 22 /November 12 to Week 23 /November 17
35 | Interior doors and Hardware | bar: Week 23 /November 14 to Week 23 /November 17
36 | HVAC finishes | bar: Week 23 /November 15 to Week 23 /November 17; Week 24 /November 21 to Week 24 /November 22; Week 25 /November-Dec 27 to Week 25 /November-Dec 28
37 | Fire Alarm finishes | bar: Week 23 /November 14 to Week 23 /November 16
38 | Electrical finishes | bar: Week 22 /November 12 to Week 23 /November 17
39 | Install mirrors | bar: Week 24 /November 20 to Week 24 /November 22
40 | Install glass partitions | bar: Week 24 /November 20 to Week 24 /November 24
41 | Inspections | bar: Week 24 /November 20 to Week 24 /November 24
42 | Appliances installation | bar: Week 24 /November 22 to Week 24 /November 24
43 | Punch List | bar: Week 25 /November-Dec 27 to Week 25 /November-Dec 1
44 | Wrap up - house cleaning | bar: Week 26 /December 4 to Week 26 /December 8; Week 27/December 11 to Week 27/December 15; Week 28 18 to Week 28 19
45 | End of construction | bar: Week 28 19